## ProjectTeam
Name | GitHub Alias | Roles
Gaupp David | gaupa1 | developer
Miletic Marko | milem2 | developer
Selvasingham Sugeelan | selvs1 | developer, scrum master
Velkov Viktor | velkv1 | developer
Janahan Sellathurai | sellj1 | developer
Alain Nippel | nippa1 | developer
Vogel, Jürgen | vgj1 | product owner
Pfarrer, Marcel | prm2 | product owner

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1 | Main-Gerüst | Projekt nach Vaadin erstellen. Views und Klassen erstellen. | high | 10 |  |  | pending | Total | 120
2 |  | Patienten-Verwaltung ?(Patientenanzeige, Patientenbericht | high | 20 |  |  | pending
3 |  | Medikamenten-Verwaltung | high | 20 |  |  | pending
4 | Content-Management | Termin-Verwaltung | high | 20 |  |  | pending | Scrum-Master | 10
5 | Authentisierung | Login/Logout Funktion | high | 10 |  |  | pending
6 | Datenbank | Datenbank Konfigurationen, Verbindung & Verwaltung | high | 25 |  |  | pending
7 | developer, scrum master | Admin-Funktion | low | 15 |  |  | pending

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Patient Model | Data model for patient record needs to be created based on standard.... | Database | Martin | Hans | medium | 2 | 2 | 0 | waiting
1.2 | 1 | Gui bauen, navigation |  | UI, Controller | Hans | Jennifer | high | 8 | 6 | 4 | work in progress
1.3 | 1 | datenbank erstellen, modelierung, integrität |  | All | Martin | Tom | high | 16 | 20 | 20 | done
2.1 | 1 | klassen erstellen, bsp Daten definieren |  | Database | Tom | Martin | low | 4 | 10 | 4 | cancelled
2.2 | 1 |  |  | Main Window | Jennifer | Martin | high | 8 | 6 | 5 | work in progress

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180